## Sheet2
Blackjack project Tasks | Predicted start date | Actual start date | End date | Total Meeting Minutes | Finished tasks check
Project Presentation project.init() | 2025-01-27 | 2025-01-27 | 2025-02-06 | 60 | TRUE
Project Presentation (Phase 1 Requirements) | 2025-02-27 | 2025-02-27 | 2025-03-06 | 210 | TRUE
Project Presentation (Phase 2 Design) | 2025-03-09 |  | 2025-04-10 |  | FALSE
Project Presentation (Phase 3 Implementation) | 2025-04-11 |  | 2025-04-17 |  | FALSE
Project Presentation (Phase 3 Testing) | 2025-04-18 |  | 2025-04-24 |  | FALSE
Project Presentation (Phase 3 Maintenance) | 2025-04-25 |  | 2025-05-01
Meeting Notes | Meeting Days | Time | Minutes | Group Memebers | Mainly worked on
init() Presentation (Discord) | 2025-02-05 | 1:oo ~ 2:00 | 60 | Mahlet Bekele | Use case
GitHub started (in person) | 2025-02-27 | 2:30 ~ 3:10 | 40 | Cristian Gonzales | Class UML
SRS Document (in person) | 2025-03-04 | 12:00 ~ 1:05 | 65 | Armand Tirado | Requirments
SRS Document (Discord) | 2025-03-04 | 6:30 ~ 8:40 | 130 | Brandon Wall | Requirments
UML Diagrams (Discord) | 2025-03-05 | 12:45 ~ 2:00 PM | 75 | Kenny Yu | Sequence Diagram